## Sheet1
| Medium Complexity | Device Count
Service Type | Service Description | < 250 | 251 - 1000 | 1001 - 5000
LOE (Hrs)
Assessment Services | Intune tenant configuration review Entra ID integration review Device enrollment / Autopilot device provisioing assessment Compliance policies review Configuration profiles review Conditional Access review Application deployment assessment Security baseline assessment Windows Update for Business review Licensing review Operational process assessment Findings report and recommendations workshop | 40 | 60 | 80
Implementation Services | Greenfield Intune + Windows Autopilot implementation
Assess | Discovery workshops; licensing/tenant readiness; current identity, device, application and security assessment; requirements confirmation; dependency identification | 20 | 40 | 60
Design | Intune architecture; Entra join strategy; Autopilot profiles; enrollment/ESP; device groups/tags; configuration/compliance policies; security baseline; Windows Update strategy; pilot approach | 40 | 60 | 80
Implement | Configure Intune foundation; enrollment restrictions; Autopilot profiles; ESP; configuration/compliance/security policies; update rings; groups/assignments; pilot deployment; production rollout and remediation | 60 | 80 | 120
Manage | Production readiness; configuration documentation; runbook; administrator KT; support handoff; project closure | 20 | 40 | 40
|  | 140 | 220 | 300